## About
Created on: | 26 Oct 25 05:21 UTC
Jira Site: | https://byui-team-af1mgfo1.atlassian.net
Jira Query: | project = P4S

## Your Jira Issues
Issue Type | Key | Summary | Assignee | Reporter | Priority | Status | Resolution | Created | Updated | Due date
Feature | P4S-34 | Integrate UART data into main service.py & UI | Kein Lika | Kein Lika | Medium | Ideas |  | 2025-10-25 22:20 | 2025-10-25 22:34 | 2025-11-11
Feature | P4S-33 | Test hardware-level UART handshake |  | Kein Lika | Medium | In Progress |  | 2025-10-25 22:19 | 2025-10-25 22:57 | 2025-10-30
Feature | P4S-32 | Implement STM32 command parser (for Pi commands) | James Green | Kein Lika | Medium | Ideas |  | 2025-10-25 22:19 | 2025-10-25 22:20 | 2025-10-30
Feature | P4S-31 | Implement STM32 UART message sending (on trigger) | Nicholas Bastian | Kein Lika | Medium | Ideas |  | 2025-10-25 22:18 | 2025-10-25 22:18 | 2025-10-30
Feature | P4S-30 | Update Pi serial_comm.py to read from UART | Kein Lika | Kein Lika | Medium | In Progress |  | 2025-10-25 22:18 | 2025-10-25 22:57 | 2025-10-30
Feature | P4S-29 | Write STM32 firmware for PIR/Reed sensor sampling | Joel Brautigam | Kein Lika | Medium | In Progress |  | 2025-10-25 22:17 | 2025-10-25 22:58 | 2025-11-08
Subtask | P4S-27 | Design and Prototype Intercom Feature (Stretch Goal) | Joel Brautigam | Joel Brautigam | Medium | Ideas |  | 2025-10-11 18:49 | 2025-10-25 22:58 | 2025-11-08
Subtask | P4S-26 | Document Alarm System Setup and Usage | Kein Lika | Joel Brautigam | Medium | Ideas |  | 2025-10-11 18:49 | 2025-10-12 00:07 | 2025-11-08
Subtask | P4S-25 | Test Alarm System Functionality | Joel Brautigam | Joel Brautigam | Medium | Ideas |  | 2025-10-11 18:49 | 2025-10-11 23:56 | 2025-11-15
Subtask | P4S-24 | Integrate Speaker Hardware with Control System | James Green | Joel Brautigam | Medium | Ideas |  | 2025-10-11 18:49 | 2025-10-11 23:56 | 2025-11-29
Subtask | P4S-23 | Implement Alarm Sound Playback Functionality | Kein Lika | Joel Brautigam | Medium | Ideas |  | 2025-10-11 18:49 | 2025-10-11 23:56 | 2025-11-01
Subtask | P4S-22 | Design Speaker System Architecture for Alarms | James Green | Joel Brautigam | Medium | Ideas |  | 2025-10-11 18:49 | 2025-10-11 23:56 | 2025-11-29
Subtask | P4S-21 | Develop Alarm Trigger Mechanism | Nicholas Bastian | Joel Brautigam | Medium | Ideas |  | 2025-10-11 18:49 | 2025-10-11 23:56 | 2025-11-08
Subtask | P4S-20 | Test and validate entry point monitoring system | Joel Brautigam | Joel Brautigam | Medium | Ideas |  | 2025-10-11 18:45 | 2025-10-11 23:55 | 2025-12-06
Subtask | P4S-19 | Develop software for sensor data acquisition and processing | Kein Lika | Joel Brautigam | Medium | Ideas |  | 2025-10-11 18:45 | 2025-10-11 23:55 | 2025-11-15
Subtask | P4S-18 | Integrate hardware components with control unit | Joel Brautigam | Joel Brautigam | Medium | Ideas |  | 2025-10-11 18:45 | 2025-10-11 23:55 | 2025-11-29
Feature | P4S-5 | Alarm System | James Green | Joel Brautigam | Medium | In Progress |  | 2025-10-11 18:34 | 2025-10-25 22:56 | 2025-12-13
Feature | P4S-4 | UI Design | Kein Lika | Joel Brautigam | Medium | Ideas |  | 2025-10-11 18:33 | 2025-10-11 23:55 | 2025-11-29
Feature | P4S-2 | Entry Point Monitoring | Nicholas Bastian | Joel Brautigam | Medium | In Progress |  | 2025-10-11 18:31 | 2025-10-25 22:56 | 2025-12-13