## Default
WBS | Issue key | Summary | Assignee | Status | Priority | Description | Due date | Start date | Issue Type
1 | P4S-2 | Entry Point Monitoring | Nicholas Bastian | In Progress | Medium | Design and implement the physical and software components of a entry point monitor system using reed switches, cameras or something of the like. | Dec 13, 2025 | Oct 6, 2025 | Feature
1.1 | P4S-18 | Integrate hardware components with control unit | Joel Brautigam | Ideas | Medium | Physically assemble and connect reed switches, cameras, and other sensors to the central control unit, ensuring reliable communication and power supply. | Nov 29, 2025 |  | Subtask
1.2 | P4S-20 | Test and validate entry point monitoring system | Joel Brautigam | Ideas | Medium | Conduct comprehensive testing of the entry point monitoring system to ensure correct detection, data processing, and alerting functionality. | Dec 6, 2025 |  | Subtask
1.3 | P4S-19 | Develop software for sensor data acquisition and processing | Kein Lika | Ideas | Medium | Implement software modules to acquire and process data from reed switches, cameras, and other sensors used in the entry point monitoring system. | Nov 15, 2025 |  | Subtask
2 | P4S-4 | UI Design | Kein Lika | Ideas | Medium | The main interface of the security system that all devices are able to connected to locally. | Nov 29, 2025 | Oct 6, 2025 | Feature
3 | P4S-5 | Alarm System | James Green | In Progress | Medium | Develop and Implement the speaker system that can be used as alarms, with a stretch goal of having a intercom apart for the system as well. | Dec 13, 2025 | Oct 6, 2025 | Feature
3.1 | P4S-22 | Design Speaker System Architecture for Alarms | James Green | Ideas | Medium | Design the overall architecture for the speaker system, including hardware and software components, to support alarm functionality. | Nov 29, 2025 |  | Subtask
3.2 | P4S-21 | Develop Alarm Trigger Mechanism | Nicholas Bastian | Ideas | Medium | Implement the software logic that triggers the speaker system to play alarm sounds based on specific events or inputs. | Nov 8, 2025 |  | Subtask
3.3 | P4S-25 | Test Alarm System Functionality | Joel Brautigam | Ideas | Medium | Conduct comprehensive testing of the alarm system to ensure correct operation, reliability, and responsiveness of the speaker alarms. | Nov 15, 2025 |  | Subtask
3.4 | P4S-24 | Integrate Speaker Hardware with Control System | James Green | Ideas | Medium | Connect and configure the speaker hardware to the central control system, ensuring reliable communication and activation. | Nov 29, 2025 |  | Subtask
3.5 | P4S-26 | Document Alarm System Setup and Usage | Kein Lika | Ideas | Medium | Create detailed documentation for the setup, configuration, and usage of the speaker alarm system for end users and maintainers. | Nov 8, 2025 |  | Subtask
3.6 | P4S-23 | Implement Alarm Sound Playback Functionality | Kein Lika | Ideas | Medium | Develop the functionality to play various alarm sounds through the speaker system, including volume control and sound selection. | Nov 1, 2025 |  | Subtask
3.7 | P4S-27 | Design and Prototype Intercom Feature (Stretch Goal) | Joel Brautigam | Ideas | Medium | Design and create a prototype for the intercom functionality as an extension of the speaker system, allowing two-way communication. | Nov 8, 2025 |  | Subtask
4 | P4S-29 | Write STM32 firmware for PIR/Reed sensor sampling | Joel Brautigam | In Progress | Medium |  | Nov 8, 2025 | Oct 6, 2025 | Feature
5 | P4S-30 | Update Pi serial_comm.py to read from UART | Kein Lika | In Progress | Medium |  | Oct 30, 2025 | Oct 6, 2025 | Feature
6 | P4S-31 | Implement STM32 UART message sending (on trigger) | Nicholas Bastian | Ideas | Medium |  | Oct 30, 2025 | Oct 6, 2025 | Feature
7 | P4S-32 | Implement STM32 command parser (for Pi commands) | James Green | Ideas | Medium |  | Oct 30, 2025 | Oct 6, 2025 | Feature
8 | P4S-33 | Test hardware-level UART handshake | Unassigned | In Progress | Medium |  | Oct 30, 2025 | Oct 6, 2025 | Feature
9 | P4S-34 | Integrate UART data into main service.py & UI | Kein Lika | Ideas | Medium |  | Nov 11, 2025 | Oct 6, 2025 | Feature